## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1(7/1) | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 - Create graphical front end of the homepage. | Matin | Closed | 7 | 7 | Day 2: 0; Day 3: 0; Day 4: 0; Day5: 0
| Task 2 - Add in backend functionality to navigate homepage. | Matin | Closed | 3 | 3 | Day 2: 3; Day 3: 0.5; Day 4: 0.5; Day5: 0
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 - Create graphical front end of the login page | Sina | Closed | 1 | 1 | Day 2: 1; Day 3: 1; Day 4: 1; Day5: 0
| Task 2 - Add in backend functionality to allow user to login with account | Sina | Closed | 0 | 0 | Day 2: 7; Day 3: 0; Day 4: 0; Day5: 0
As a user I want to see Shape Id above shapes in a window that’s a fixed size so I know what I’m doing. | Task 1 - Show Shape ID
| Task 2 - Create a Qwidget RenderArea of 1000x500 | Arthur | Closed | 3 |  | Day 8: 3
As a user I would like to read in shape data from a text file so that I can have a library of shapes. | Task1 - create vector for shapes | Arthur | Closed | 14 | 9 | Day 3: 3; Day5: 2
| Task 2- Create Shape Class | Arthur | Closed | 18 |  | Day 8: 4; Day 9: 4
| Task3 - Create Derived Classes | TEAM | Closed | 6 |  | Day 8: 6
| Task 4- Create ShapeBuffer for file read | Arthur | Open | 6 |  | Day 12: 2; Day 14: 4
As an Admin, I want to move shapes around the screen so that I can arrange them however I want.
| Total |  |  | 58 | 20 | 11 | 4.5 | 1.5 | 2 | 0 | 0 | 13 | 4 | 0 | 0 | 2 | 0 | 4
|  |  | Remaining Hours | 58 | 38 | 27 | 22.5 | 21 | 19 | 19 | 19 | 6 | 2 | 2 | 2 | 0 | 0 | -4
Sprint Goal
Create a functinal version of our program with basic functionality.

## Sprint 2
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1(7/1) | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
45
6
|  |  |  | 45 |  | Day 2: 6; Day5: 4
|  |  |  | 45 |  | Day 3: 6
| Total |  |  | 135 | 0 | Day 2: 6; Day 3: 6; Day 4: 6; Day5: 4
Sprint Goal
Create a functinal version of our program with basic functionality.