## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 - Create graphical front end of the homepage. | Matin | Closed | 7 | Day 1: 7; Day 2: 0; Day 3: 0; Day 4: 0; Day5: 0
| Task 2 - Add in backend functionality to navigate homepage. | Matin | Closed | 3 | Day 1: 3; Day 2: 3; Day 3: 0.5; Day 4: 0.5; Day5: 0
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 - Create graphical front end of the login page | Sina | Closed | 1 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 1; Day5: 0
| Task 2 - Add in backend functionality to allow user to login with account | Sina | Closed | 0 | Day 1: 0; Day 2: 7; Day 3: 0; Day 4: 0; Day5: 0
As a user I want to see Shape Id above shapes in a window that’s a fixed size so I know what I’m doing. | Task 1 - Show Shape ID on canvas |  | Closed
| Task 2- organize sequentially by Shape ID on the tree widget UI window as they are drawn, the tree roots will display each shape's sequential ID and their information and properties will be shown as tree children | Matin | Closed | 8 | Day 12: 3; Day 13: 2; Day 14: 7
| Task 3 - Create a Qwidget RenderArea of 1000x500 | Arthur | Closed | 3 | Day 8: 3
As a user I would like to read in shape data from a text file so that I can have a library of shapes. | Task1 - create vector for shapes | Arthur | Closed | 14 | Day 1: 9; Day 3: 3; Day5: 2
| Task 2- Create Shape Class | Arthur/Matin | Closed | 18 |  | 1 | 3 | 3 |  | 3 | 4 | 5 | 4 | 1 |  |  | 1
| Task3 - Create Derived Classes | TEAM | Closed | 6 | Day 3: 2; Day 4: 2; Day 8: 6
| Task 4- Create ShapeBuffer for file read | Arthur | Closed | 6 | Day 12: 2; Day 14: 4
As an Admin, I want to move shapes around the screen so that I can arrange them however I want. | Task 1 - Create move () functions for derived classes and UI movement | Arthur/William/Alex/Matin | Closed | 6 | Day 3: 1; Day 4: 1; Day 8: 2; Day 10: 6
As a user I want to be able to use a palette to draw shapes so that I can change how the render area looks | Task 1 - Create Palette Widget | Alex | Closed | 2 | Day 2: 2
| Task 2 - Palette Functionality | Alex | Closed | 5 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 2
As a user I want to select a custom background and shape color so that I can change how the render area looks | Task 1 - Palette controls shape and background color | Alex | Closed | 3 | Day 1: 2; Day 2: 1
As a developer I want to be able to access all options through a toolbar so that I can easily navigate the menu | Task 1 - Menu option | TEAM | Closed | 1 | bar: Day 1; Day 13
As a user I want to be able to see info about all shapes so that I am more enagaged with the program | Task 1 - Write Shape Info Tree Widget functions and implement functionality | Matin | Closed | 5 | Day 11: 1; Day 13: 2; Day 14: 3
| Task 2- Create show info functionality in toolbar widger in mainwindow and in window bar | Matin | closed | 2 | Day 13: 3; Day 14: 1
As a user I want to be able to see contact information of the company so that I can learn more about the production team | Task 1 - Create Contact Widget | Cena | Closed | 1 | Day 1: 1; Day5: 2
As a user I want to be able write shapes to file in an organized fashion so that I can save data | Task 1 - Selection Sort | Oliver | Closed | 7 | Day 6: 3; Day 9: 4
As a user I want to be able to quit the program through an option in a menu so that I can leave the program | Task 1 - Quit Functionality | Alex | Closed | 1 | bar: Day 1
As a user I want to be able to move shapes by ID so that I can change where shapes render | Task 1 - Shape Move Functionality | Cena/Alex | Closed | 4 | Day 1: 1; Day 2: 1; Day 3: 2
As an admin I want to be able to move shapes by clicking and dropping so that I can change where shapes render | Task 1 - Clicking Functionality | Alex | Closed | 2 | Day 1: 2
As an authenticated website visitor I want to be able to view webpage through link in program so that I can communicate with the development team | Task 1 - Link functionality | Sina | Closed | 1 | bar: Day 2
|  |  |  | 106 | 29 | 18 | 13.5 | 1.5 | 4 | 6 | 4 | 16 | 8 | 7 | 1 | 5 | 9 | 15
Sprint Goal | Total |  | Remaining Hours | 58 | 77 | 59 | 45.5 | 44 | 40 | 34 | 30 | 14 | 6 | -1 | -2 | -7 | -16 | -31
Create a functinal version of our program with basic functionality.

## Sprint 2
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1(7/15) | Day2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Day 8 | Day 9 7/23 DUE DATE
As a user I would like to read in shape data from a text file so that I can have a library of shapes | Task 4- Create ShapeBuffer for file read | Arthur | Closed |  | 4 |  |  |  | 1
| Task 5- Read a file in to buffer, then to shapes | Arthur | Closed |  | 2
As a user I want to save changes so that I don’t lose my work. | Task 1 - Load shapes into buffer | Arthur | Closed | 10 |  |  |  | 5
| Task 2 - Write buffer to text file | Arthur/Blake | Closed | 10 |  |  |  | 3 | 8
As a user I want to see current time and elapsed time after finishing my session. | Task 1 - Display time in window title
| Task 2 - Algorithm for finding time difference | William | Closed | 1 | 1
As a user I want to be able to see info about all shapes so that I am more enagaged with the program | Task 1 - Write Shape Info Tree Widget functions and implement functionality | Matin | closed |  |  |  |  | 3
As a user I want to see Shape Id above shapes in a window that’s a fixed size so I know what I’m doing. | Task 2- organize sequentially by Shape ID on the tree widget UI window as they are drawn, the tree roots will display each shape's sequential ID and their information and properties will be shown as tree children | Matin/Sina | Closed | 8 | 2 |  |  | 3 | 5 | 2
| Total |  |  | 29 | 9 | 0 | 0 | 8 | 14 | 2 | 0 | 0 | 0
|  |  | Remaining Hours | 58 | 20 | 20 | 20 | 12 | -2 | -4 | -4 | -4 | -4
Sprint Goal
Create a functinal version of our program with basic functionality.