## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 - Create graphical front end of the homepage. | Matin | Closed | 7 | Day 1: 7; Day 2: 0; Day 3: 0; Day 4: 0; Day5: 0
| Task 2 - Add in backend functionality to navigate homepage. | Matin | Closed | 3 | Day 1: 3; Day 2: 3; Day 3: 0.5; Day 4: 0.5; Day5: 0
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 - Create graphical front end of the login page | Sina | Closed | 1 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 1; Day5: 0
| Task 2 - Add in backend functionality to allow user to login with account | Sina | Closed | 0 | Day 1: 0; Day 2: 7; Day 3: 0; Day 4: 0; Day5: 0
As a user I want to see Shape Id above shapes in a window that’s a fixed size so I know what I’m doing. | Task 1 - Show Shape ID
| Task 2 - Create a Qwidget RenderArea of 1000x500 | Arthur | Closed | 3 | Day 8: 3
As a user I would like to read in shape data from a text file so that I can have a library of shapes. | Task1 - create vector for shapes | Arthur | Closed | 14 | Day 1: 9; Day 3: 3; Day5: 2
| Task 2- Create Shape Class | Arthur | Closed | 18 | Day 8: 4; Day 9: 4
| Task3 - Create Derived Classes | TEAM | Closed | 6 | Day 8: 6
| Task 4- Create ShapeBuffer for file read | Arthur | Closed | 6 | Day 12: 2; Day 14: 4
As an Admin, I want to move shapes around the screen so that I can arrange them however I want.
As a user I want to be able to use a palette to draw shapes so that I can change how the render area looks | Task 1 - Create Palette Widget | Alex | Closed | 2 | Day 2: 2
| Task 2 - Palette Functionality | Alex | Closed | 5 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 2
As a user I want to select a custom background and shape color so that I can change how the render area looks | Task 1 - Palette controls shape and background color | Alex | Closed | 3 | Day 1: 2; Day 2: 1
As a developer I want to be able to access all options through a toolbar so that I can easily navigate the menu | Task 1 - Menu option | TEAM | Closed | 1 | bar: Day 1
As a user I want to be able to see info about all shapes so that I am more enagaged with the program | Task 1 - Create Contact Widget | Cena | Closed | 5 | Day 1: 1; Day 3: 2; Day5: 2
As a user I want to be able to see contact information of the company so that I can learn more about the production team | Task 1 - Create Contact Widget | Cena | Closed | 1 | bar: Day 1
As a user I want to be able write shapes to file in an organized fashion so that I can save data | Task 1 - Selection Sort | Oliver | Closed | 7 | Day 6: 3; Day 9: 4
As a user I want to be able to quit the program through an option in a menu so that I can leave the program | Task 1 - Quit Functionality | Alex | Closed | 1 | bar: Day 1
As a user I want to be able to move shapes by ID so that I can change where shapes render | Task 1 - Shape Move Functionality | Cena/Alex | Closed | 4 | Day 1: 1; Day 2: 1; Day 3: 2
As an admin I want to be able to move shapes by clicking and dropping so that I can change where shapes render | Task 1 - Clicking Functionality | Alex | Closed | 2 | Day 1: 2
As an authenticated website visitor I want to be able to view webpage through link in program so that I can communicate with the development team | Task 1 - Link functionality | Sina | Closed | 1 | bar: Day 2
|  |  |  | 90 | 30 | 17 | 9.5 | 1.5 | 4 | 3 | 0 | 13 | 8 | 0 | 0 | 2 | 0 | 4
Sprint Goal | Total |  | Remaining Hours | 58 | 60 | 43 | 33.5 | 32 | 28 | 25 | 25 | 12 | 4 | 4 | 4 | 2 | 2 | -2
Create a functinal version of our program with basic functionality.

## Sprint 2
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1(7/15) | Day2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Day 8 | Day 9 7/23 DUE DATE
As a user I would like to read in shape data from a text file so that I can have a library of shapes | Task 4- Create ShapeBuffer for file read | Arthur | Closed |  | 4 |  |  |  | 1
| Task 5- Read a file in to buffer, then to shapes | Arthur | Closed |  | 2
As a user I want to save changes so that I don’t lose my work. | Task 1 - Load shapes into buffer | Arthur | Closed | 10 |  |  |  | 5
| Task 2 - Write buffer to text file | Arthur/Blake | Closed | 10 |  |  |  | 3 | 8
| Total |  |  | 20 | 6 | 0 | 0 | 8 | 9 | 0 | 0 | 0 | 0
|  |  | Remaining Hours | 58 | 14 | 14 | 14 | 6 | -3 | -3 | -3 | -3 | -3
Sprint Goal
Create a functinal version of our program with basic functionality.