## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 - Create graphical front end of the homepage. | Matin | Closed | 7 | 7 | 0 | 0 | 0 | 0
| Task 2 - Add in backend functionality to navigate homepage. | Matin | Closed | 3 | 3 | 3 | 0.5 | 0.5 | 0
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 - Create graphical front end of the login page | Sina | Closed | 1 | 1 | 1 | 1 | 1 | 0
| Task 2 - Add in backend functionality to allow user to login with account | Sina | Closed | 0 | 0 | 7 | 0 | 0 | 0
As a / an website visitor I want to be able to register for an account so that I can login and gain all the benefits of being an authenticated user | Task 1 - Create front end graphical registration page
Task 2 - Create back end registration functionality.
As a / an authenticated website visitor I want to be able to manage my profile details so that I can update incorrect or changed details and view current records | Task 1 - Create front end graphical profile management page
Task 2 - Create back end profile updating functionality
As a / an authenticated website visitor I want to be able to log out of the website so that my private information is kept secure when accessing the site on a shared computer | Task 1 - Create log out button on main application page
Task 2 - Create log out functionality that signs the user out of account
As a / an website visitor I want to be able to reset my password so that I can still access my account even if I forget my password | Task 1 - Create button that allows user to reset password on login page
Task 2 - Create button functionality that prompts user to answer security questions to reset password
As a / an website visitor I want to be able to recover my username so that I can access my account if I have forgotten my username | Task 1 - Create button that allows user to recover their username on login page
Task 2 - Create button functionality that prompts user to answer security questions to recover username
As a / an authenticated website visitor I want to see a customised homepage so that I am more enagaged with the website | Task 1 - Create options page for homepage customization
Task 2 - Update homepage with selected widgets, if none selected automatically insert information
| Total |  |  | 11 | 11 | 11 | 1.5 | 1.5 | 0
Sprint Goal
Create a functinal version of our program with basic functionality.