## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 - Create graphical front end of the homepage. | Matin | Closed | 7 | 7 | 0 | 0 | 0 | 0
| Task 2 - Add in backend functionality to navigate homepage. | Matin | Closed | 3 | 3 | 3 | 0.5 | 0.5 | 0
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 - Create graphical front end of the login page | Sina | Closed | 1 | 1 | 1 | 1 | 1 | 0
| Task 2 - Add in backend functionality to allow user to login with account | Sina | Closed | 0 | 0 | 7 | 0 | 0 | 0
As a user I want to see Shape Id above shapes in a window that’s a fixed size so I know what I’m doing.
| Total |  |  | 11 | 11 | 11 | 1.5 | 1.5 | 0
Sprint Goal
Create a functinal version of our program with basic functionality.